## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2225-swen-261-02-h (404) Team Not Found
Testing Team Name | 2225-swen-261-02-d-Mental Bake Down

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. |  |  | Pass | SA(Team 4)
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. |  |  | Pass
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. |  |  | Pass
| Given that I am on the products page when there are products in the inventory then I see each product and short description. |  |  | Pass
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. |  |  | Pass
As a user I want to add a Product to my Shopping Cart | Given that I am on the Products page when I have not added the Product to my Shopping Cart and the Product is in stock then I must see a means to add the Product to my Shopping Cart. |  |  | Fail | note: there are no are items in cart even if there is a message displayed. No access to cart if not logged in and shows low stock with "7" in stock for error message. When item added to cart it immediately reduces stock. Cannot checkout too
| Given that I am on the Products page when I have added the Product to my Shopping Cart and the Product is in stock then I must still be able to add the Product to my Shopping Cart. |  |  | Fail | Makes new item as admin - shows added to cart although not logged in and can access cart link
| Given that I am on the Products page when I have not added the Product to my Shopping Cart and the Product is not in stock then I must be not able to add the Product to my Shopping Cart. |  |  | Fail | can access any url when not logged in if known( don't know if this is important)
| Given that I am on the Products page when I have added the Product to my Shopping Cart and the Product is not in stock then I must not be able to add the Product to my Shopping Cart. |  |  | Pass
| Given that I am on the Products page when I am not logged in then I must not be able to add a Product to the shopping cart |  |  | Fail | shows added to cart although not logged in and can access cart link
As a user I want to add be able to Login to my account | Given that I am on the e-store site when I am not on the Login page then I must see a means to navigate to the Login page. |  |  | Pass
| Given that I am not on the e-store site when I choose the Login page then I am taken to the Login page. |  |  | Pass
| Given that I am on the Login page when I am not logged in then I must see a means to enter my login information and submit it. |  |  | Pass
| Given that I am on the e-store site when I am logged in then I must not be able to see a means to login again. |  |  | Pass
| Given that I am on the Login page when I have inputted the wrong account info then I must not be logged in and prompted to enter the correct info |  |  | Pass
| Given that I am on the Login page when I have inputted the correct account info then I must be logged in and brought to the estore site |  |  | Pass
As a user I want to be able to Create an acount | Given that I am on the e-store site when I am not on the Create account page and when I am not logged in then I must see a means to navigate to the Create account page. |  |  | Pass
| Given that I am on the estore-page when I am not logged in and I choose the Create account page then I am take to the Create account page |  |  | Pass
| Given that I am on the Create account page when I have entered mu information then I must see a means to create my account |  |  | Pass
| Given that I am on the estore-site when I have created my Account then I must be logged into my account and not have a means to create a new account |  |  | Pass
As an admin I want to be able to modify the details of a Product | Given that I am on the estore-site when I am not logged in as an Admin then I must not be able to edit a Product |  |  | Pass
| Given that I am on the estore-site when I am logged in as an Admin then I must see some means to edit a Product |  |  | Pass
| Given that I am on the edit products page when I am logged in as an Admin then I must be able to change the name, price, quantity, and image URL. |  |  | Pass
| Given that I am on the edit products page when I am logged in as an Admin then I must be able to delete a Product |  |  | Pass
As an admin I want to be able to create a new Product | Given that I am on the estore-site when I am not logged in as an Admin then I must not be able to create a new Product |  |  | Pass
| Given that I am on the estore-site when I am logged in as an Admin then I must see some means to create a new Product |  |  | Pass
| Given that I am on the create products page when I am logged in as an Admin then I must be able to create a new product with a name, price, quantity, product type, and image URL. |  |  | Pass
As a user I want to be able to edit my Account Info | Given that I am on the estore-site when I am logged in then I must see a means of accessing my Account |  |  | Pass
| Given that I am on the estore site when I am logged in and I choose the Account page then I must go to the Account page |  |  | Pass
| Given that I am on the Account page when I am logged in then I must see a means to change my password |  |  | Pass | Can edit password and login works perffectly.
| Given that I am on the Account page when I am logged in then I must see a means to add my Payment Info |  |  | Pass
| Given that I am on the Account page when I am logged in then I must see a means to add my Address Info |  |  | Pass | Note: cannot edit any shipping info
| Given that I am on the Account page when I am logged in then I must see a means to delete my Account |  |  | Pass | Deletes account properly.